## Sheet1
Module ID | VSL ID | BOM under test | Test Name | Count | Start Date | Done (Hr) | Remaining (Hr) | Done (Cycles) | Remaining (Cycles) | Tentative End Date | Lag | Type | Cycle Time (Hr) | Total Duration (Hr) | Actual End Date | time axis 2025-01-01 to 2069-10-24
24166832 | VSL202425316 | M10R HYPERSOL (AMPIN) | PID | 288 | 2025-02-05 | [10 empty] | 2025-02-05: 12; 2025-02-06: 24; 2025-02-07: 24; 2025-02-08: 24; 2025-02-09: 24; 2025-02-10: 24; 2025-02-11: 24; 2025-02-12: 24; 2025-02-13: 24; 2025-02-14: 24; 2025-02-15: 24; 2025-02-16: 24; 2025-02-17: 12
24166841 | VSL202425317 | M10R HYPERSOL (AMPIN) | PID | 288 | 2025-02-05 | [10 empty] | 2025-02-05: 12; 2025-02-06: 24; 2025-02-07: 24; 2025-02-08: 24; 2025-02-09: 24; 2025-02-10: 24; 2025-02-11: 24; 2025-02-12: 24; 2025-02-13: 24; 2025-02-14: 24; 2025-02-15: 24; 2025-02-16: 24; 2025-02-17: 12
24166861 | VSL202425318 | M10R HYPERSOL (AMPIN) | TC | 600 | 2025-02-04 | [9 empty] | 2025-03-29 | 2025-02-04: 18; 2025-02-05: 24; 2025-02-06: 24; 2025-02-07: 24; 2025-02-08: 24; 2025-02-09: 24; 2025-02-10: 24; 2025-02-11: 24; 2025-02-12: 24; 2025-02-13: 24; 2025-02-14: 24; 2025-02-15: 24; 2025-02-16: 24; 2025-02-17: 24; 2025-02-18: 24; 2025-02-19: 24; 2025-02-20: 24; 2025-02-21: 24; 2025-02-22: 24; 2025-02-23: 24; 2025-02-24: 24; 2025-02-25: 24; 2025-02-26: 24; 2025-02-27: 24; 2025-02-28: 24; 2025-03-01: 24; 2025-03-02: 24; 2025-03-03: 24; 2025-03-04: 24; 2025-03-05: 24; 2025-03-06: 24; 2025-03-07: 24; 2025-03-08: 24; 2025-03-09: 24; 2025-03-10: 24; 2025-03-11: 24; 2025-03-12: 24; 2025-03-13: 24; 2025-03-14: 24; 2025-03-15: 24; 2025-03-16: 24; 2025-03-17: 24; 2025-03-18: 24; 2025-03-19: 24; 2025-03-20: 24; 2025-03-21: 24; 2025-03-22: 24; 2025-03-23: OFF; 2025-03-24: 24; 2025-03-25: 24; 2025-03-26: 24; 2025-03-27: 24; 2025-03-28: 24; 2025-03-29: 18
24166862 | VSL202425319 | M10R HYPERSOL (AMPIN) | TC | 600 | 2025-02-04 | [9 empty] | 2025-03-29 | 2025-02-04: 18; 2025-02-05: 24; 2025-02-06: 24; 2025-02-07: 24; 2025-02-08: 24; 2025-02-09: 24; 2025-02-10: 24; 2025-02-11: 24; 2025-02-12: 24; 2025-02-13: 24; 2025-02-14: 24; 2025-02-15: 24; 2025-02-16: 24; 2025-02-17: 24; 2025-02-18: 24; 2025-02-19: 24; 2025-02-20: 24; 2025-02-21: 24; 2025-02-22: 24; 2025-02-23: 24; 2025-02-24: 24; 2025-02-25: 24; 2025-02-26: 24; 2025-02-27: 24; 2025-02-28: 24; 2025-03-01: 24; 2025-03-02: 24; 2025-03-03: 24; 2025-03-04: 24; 2025-03-05: 24; 2025-03-06: 24; 2025-03-07: 24; 2025-03-08: 24; 2025-03-09: 24; 2025-03-10: 24; 2025-03-11: 24; 2025-03-12: 24; 2025-03-13: 24; 2025-03-14: 24; 2025-03-15: 24; 2025-03-16: 24; 2025-03-17: 24; 2025-03-18: 24; 2025-03-19: 24; 2025-03-20: 24; 2025-03-21: 24; 2025-03-22: 24; 2025-03-23: OFF; 2025-03-24: 24; 2025-03-25: 24; 2025-03-26: 24; 2025-03-27: 24; 2025-03-28: 24; 2025-03-29: 18
24166863 | VSL202425320 | M10R HYPERSOL (AMPIN) | HF | 30
24166864 | VSL202425321 | M10R HYPERSOL (AMPIN) | HF | 30
24166865 | VSL202425322 | M10R HYPERSOL (AMPIN) | DH | 3000 | 2025-04-02 | [10 empty] | 2025-04-02: 8; 2025-04-03: 24; 2025-04-04: 24; 2025-04-05: 24; 2025-04-06: 24; 2025-04-07: 24; 2025-04-08: 24; 2025-04-09: 24; 2025-04-10: 24; 2025-04-11: 24; 2025-04-12: 24; 2025-04-13: 24; 2025-04-14: 24; 2025-04-15: 24; 2025-04-16: 12; 2025-04-17: 24; 2025-04-18: 9; 2025-04-19: off; 2025-04-20: off; 2025-04-21: off; 2025-04-22: off; 2025-04-23: off; 2025-04-24: off; 2025-04-25: 24; 2025-04-26: 24; 2025-04-27: 24; 2025-04-28: 24; 2025-04-29: 24; 2025-04-30: 24; 2025-05-01: OFF; 2025-05-02: 12; 2025-05-03: 24; 2025-05-04: 24; 2025-05-05: 24; 2025-05-06: 24; 2025-05-07: 24; 2025-05-08: 24; 2025-05-09: 24; 2025-05-10: 24; 2025-05-11: 24; 2025-05-12: 24; 2025-05-13: 24; 2025-05-14: 24; 2025-05-15: 24; 2025-05-16: 24; 2025-05-17: 24; 2025-05-18: 9; 2025-05-19: off; 2025-05-20: off; 2025-05-21: off; 2025-05-22: off; 2025-05-23: off; 2025-05-24: off; 2025-05-25: 6; 2025-05-26: 24; 2025-05-27: 24; 2025-05-28: 24; 2025-05-29: 24; 2025-05-30: 24; 2025-05-31: off; 2025-06-01: 24; 2025-06-02: 24; 2025-06-03: 24; 2025-06-04: 24; 2025-06-05: 24; 2025-06-06: 9; 2025-06-07: off; 2025-06-08: 8; 2025-06-09: 24
24166867 | VSL202425323 | M10R HYPERSOL (AMPIN) | DH | 3000 | 2025-04-02 | [10 empty] | 2025-04-02: 8; 2025-04-03: 24; 2025-04-04: 24; 2025-04-05: 24; 2025-04-06: 24; 2025-04-07: 24; 2025-04-08: 24; 2025-04-09: 24; 2025-04-10: 24; 2025-04-11: 24; 2025-04-12: 24; 2025-04-16: 12; 2025-04-17: 24; 2025-04-18: 9; 2025-04-19: off; 2025-04-20: off; 2025-04-21: off; 2025-04-22: off; 2025-04-23: off; 2025-04-24: off; 2025-04-25: 24; 2025-04-26: 24; 2025-04-27: 24; 2025-04-28: 24; 2025-04-29: 24; 2025-04-30: 24; 2025-05-01: OFF; 2025-05-02: 12; 2025-05-03: 24; 2025-05-04: 24; 2025-05-05: 24; 2025-05-06: 24; 2025-05-07: 24; 2025-05-08: 24; 2025-05-09: 24; 2025-05-10: 24; 2025-05-11: 24; 2025-05-12: 24; 2025-05-13: 24; 2025-05-14: 24; 2025-05-15: 24; 2025-05-16: 24; 2025-05-17: 24; 2025-05-18: 9; 2025-05-19: off; 2025-05-20: off; 2025-05-21: off; 2025-05-22: off; 2025-05-23: off; 2025-05-24: off; 2025-05-25: 6; 2025-05-26: 24; 2025-05-27: 24; 2025-05-28: 24; 2025-05-29: 24; 2025-05-30: 24; 2025-05-31: off; 2025-06-01: 24; 2025-06-02: 24; 2025-06-03: 24; 2025-06-04: 24; 2025-06-05: 24; 2025-06-06: 9; 2025-06-07: off; 2025-06-08: 8; 2025-06-09: 24
24166869 | VSL202425324 | M10R HYPERSOL (AMPIN) | LID | 60
24166889 | VSL202425325 | M10R HYPERSOL (AMPIN) | LID | 60
24166896 | VSL202425326 | M10R HYPERSOL (AMPIN) | LID | 60
24306368 | VSL202425280 | QC Solar Blocking Diode Reliability testing | LID | 60 | 2025-01-20
24308189 | VSL202425283 | UKTR Blocking Diode Reliability testing | LID | 60 | 2025-01-20
24303936 | VSL202425289 | Solarspace 8.4 Wp TOPCon + HTARC | DH | 1000 | 2025-02-10 | [10 empty] | 2025-02-10: 6; 2025-02-11: 24; 2025-02-12: 24; 2025-02-13: 24; 2025-02-14: 24; 2025-02-15: 24; 2025-02-16: 24; 2025-02-17: 23; 2025-02-18: 24; 2025-02-19: 24; 2025-02-20: 24; 2025-02-21: 24; 2025-02-22: 24; 2025-02-23: 24; 2025-02-24: 24; 2025-02-25: 24; 2025-02-26: 24; 2025-02-27: 24; 2025-02-28: 24; 2025-03-01: 24; 2025-03-02: 24; 2025-03-03: 24; 2025-03-04: 24; 2025-03-05: 24; 2025-03-06: 24; 2025-03-07: 24; 2025-03-08: 24; 2025-03-09: 24; 2025-03-10: 12; 2025-03-11: OFF; 2025-03-12: OFF; 2025-03-13: OFF; 2025-03-14: OFF; 2025-03-15: OFF; 2025-03-16: OFF; 2025-03-17: 10; 2025-03-18: OFF; 2025-03-19: OFF; 2025-03-20: OFF; 2025-03-21: 9; 2025-03-22: 24; 2025-03-23: 24; 2025-03-24: 24; 2025-03-25: 24; 2025-03-26: 16; 2025-03-27: 24; 2025-03-28: 24; 2025-03-29: 24; 2025-03-30: 16; 2025-03-31: 24; 2025-04-01: 24; 2025-04-02: 21; 2025-04-03: 24; 2025-04-04: 23
24303937 | VSL202425290 | Solarspace 8.4 Wp TOPCon + HTARC | TC | 200 | 2025-02-10 | [10 empty] | 2025-02-10: 7; 2025-02-11: 24; 2025-02-12: 24; 2025-02-13: 24; 2025-02-14: 24; 2025-02-15: 24; 2025-02-16: 24; 2025-02-17: 23; 2025-02-18: 24; 2025-02-19: 8; 2025-02-20: OFF; 2025-02-21: OFF; 2025-02-22: OFF; 2025-02-23: OFF; 2025-02-24: OFF; 2025-02-25: OFF; 2025-02-26: 12; 2025-02-27: 24; 2025-02-28: 24; 2025-03-01: 24; 2025-03-02: 24; 2025-03-03: 24; 2025-03-04: 24; 2025-03-05: 24; 2025-03-06: 5; 2025-03-07: OFF; 2025-03-08: OFF; 2025-03-09: 5; 2025-03-10: 12; 2025-03-11: OFF; 2025-03-12: OFF; 2025-03-13: OFF; 2025-03-14: OFF; 2025-03-15: OFF; 2025-03-16: OFF; 2025-03-17: 6; 2025-03-18: OFF; 2025-03-19: OFF; 2025-03-20: OFF; 2025-03-21: OFF; 2025-03-22: OFF; 2025-03-23: OFF; 2025-03-24: 6
24401571 | VSL202425330 | Valeo 0.24mm INTC ribbon trial (For TOPCon) | DH | 1000 | 2025-02-10 | [10 empty] | 2025-02-10: 6; 2025-02-11: 24; 2025-02-12: 24; 2025-02-13: 24; 2025-02-14: 24; 2025-02-15: 24; 2025-02-16: 24; 2025-02-17: 23; 2025-02-18: 24; 2025-02-19: 24; 2025-02-20: 24; 2025-02-21: 24; 2025-02-22: 24; 2025-02-23: 24; 2025-02-24: 24; 2025-02-25: 24; 2025-02-26: 24; 2025-02-27: 24; 2025-02-28: 24; 2025-03-01: 24; 2025-03-02: 24; 2025-03-03: 24; 2025-03-04: 24; 2025-03-05: 24; 2025-03-06: 24; 2025-03-07: 24; 2025-03-08: 24; 2025-03-09: 24; 2025-03-10: 12; 2025-03-11: OFF; 2025-03-12: OFF; 2025-03-13: OFF; 2025-03-14: OFF; 2025-03-15: OFF; 2025-03-16: OFF; 2025-03-17: 10; 2025-03-18: OFF; 2025-03-19: OFF; 2025-03-20: OFF; 2025-03-21: 9; 2025-03-22: 24; 2025-03-23: 24; 2025-03-24: 24; 2025-03-25: 24; 2025-03-26: 16; 2025-03-27: 24; 2025-03-28: 24; 2025-03-29: 24; 2025-03-30: 16; 2025-03-31: 24; 2025-04-01: 24; 2025-04-02: 21; 2025-04-03: 24; 2025-04-04: 23
24401574 | VSL202425331 | Valeo 0.24mm INTC ribbon trial (For TOPCon) | TC | 200 | 2025-03-04 | [9 empty] | 2025-05-26 | 2025-03-04: 7; 2025-03-05: 24; 2025-03-06: 5; 2025-03-07: OFF; 2025-03-08: OFF; 2025-03-09: 5; 2025-03-10: 12; 2025-03-11: OFF; 2025-03-12: OFF; 2025-03-13: OFF; 2025-03-14: OFF; 2025-03-15: OFF; 2025-03-16: OFF; 2025-03-17: 6; 2025-03-18: OFF; 2025-03-19: OFF; 2025-03-20: OFF; 2025-03-21: OFF; 2025-03-22: OFF; 2025-03-23: OFF; 2025-03-24: 6; 2025-03-25: OFF; 2025-03-26: OFF; 2025-03-27: OFF; 2025-03-28: OFF; 2025-03-29: OFF; 2025-03-30: OFF; 2025-03-31: OFF; 2025-04-01: OFF; 2025-04-02: OFF; 2025-04-03: OFF; 2025-04-04: OFF; 2025-04-05: OFF; 2025-04-06: OFF; 2025-04-07: OFF; 2025-04-08: OFF; 2025-04-09: OFF; 2025-04-10: OFF; 2025-04-11: OFF; 2025-04-26: 355
51816376 | VSL202425327 | Glass rainbow/visual damage inspection test (FAB 3 module) | DH | 1000 | 2025-02-16 | [10 empty] | 2025-02-16: 6; 2025-02-17: 23; 2025-02-18: 24; 2025-02-19: 24; 2025-02-20: 24; 2025-02-21: 24; 2025-02-22: 24; 2025-02-23: 24; 2025-02-24: 24; 2025-02-25: 24; 2025-02-26: 24; 2025-02-27: 24; 2025-02-28: 24; 2025-03-01: 24; 2025-03-02: 24; 2025-03-03: 24; 2025-03-04: 24; 2025-03-05: 24; 2025-03-06: 24; 2025-03-07: 24; 2025-03-08: 24; 2025-03-09: 24; 2025-03-10: 12; 2025-03-11: OFF; 2025-03-12: OFF; 2025-03-13: OFF; 2025-03-14: OFF; 2025-03-15: OFF; 2025-03-16: OFF; 2025-03-17: 10; 2025-03-18: OFF; 2025-03-19: OFF; 2025-03-20: OFF; 2025-03-21: 9; 2025-03-22: 24; 2025-03-23: 24; 2025-03-24: 24; 2025-03-25: 24; 2025-03-26: 16; 2025-03-27: 24; 2025-03-28: 24; 2025-03-29: 24; 2025-03-30: 16; 2025-03-31: 24; 2025-04-01: 24; 2025-04-02: 21; 2025-04-03: 24; 2025-04-04: 24; 2025-04-05: 24; 2025-04-06: 24; 2025-04-07: 24; 2025-04-08: 23; 2025-04-09: 24; 2025-04-10: 24
51817126 | VSL202425328 | Glass rainbow/visual damage inspection test (FAB 3 module) | DH | 1000 | 2025-02-16 | [10 empty] | 2025-02-16: 6; 2025-02-17: 23; 2025-02-18: 24; 2025-02-19: 24; 2025-02-20: 24; 2025-02-21: 24; 2025-02-22: 24; 2025-02-23: 24; 2025-02-24: 24; 2025-02-25: 24; 2025-02-26: 24; 2025-02-27: 24; 2025-02-28: 24; 2025-03-01: 24; 2025-03-02: 24; 2025-03-03: 24; 2025-03-04: 24; 2025-03-05: 24; 2025-03-06: 24; 2025-03-07: 24; 2025-03-08: 24; 2025-03-09: 24; 2025-03-10: 12; 2025-03-11: OFF; 2025-03-12: OFF; 2025-03-13: OFF; 2025-03-14: OFF; 2025-03-15: OFF; 2025-03-16: OFF; 2025-03-17: 10; 2025-03-18: OFF; 2025-03-19: OFF; 2025-03-20: OFF; 2025-03-21: 9; 2025-03-22: 24; 2025-03-23: 24; 2025-03-24: 24; 2025-03-25: 24; 2025-03-26: 16; 2025-03-27: 24; 2025-03-28: 24; 2025-03-29: 24; 2025-03-30: 16; 2025-03-31: 24; 2025-04-01: 24; 2025-04-02: 21; 2025-04-03: 24; 2025-04-04: 24; 2025-04-05: 24; 2025-04-06: 24; 2025-04-07: 24; 2025-04-08: 23; 2025-04-09: 24; 2025-04-10: 24
51814914 | VSL202425329 | Glass rainbow/visual damage inspection test (FAB 3 module) | DH | 1000 | 2025-02-10 | [10 empty] | 2025-02-10: 6; 2025-02-11: 24; 2025-02-12: 24; 2025-02-13: 24; 2025-02-14: 24; 2025-02-15: 24; 2025-02-16: 24; 2025-02-17: 23; 2025-02-18: 24; 2025-02-19: 24; 2025-02-20: 24; 2025-02-21: 24; 2025-02-22: 24; 2025-02-23: 24; 2025-02-24: 24; 2025-02-25: 24; 2025-02-26: 24; 2025-02-27: 24; 2025-02-28: 24; 2025-03-01: 24; 2025-03-02: 24; 2025-03-03: 24; 2025-03-04: 24; 2025-03-05: 24; 2025-03-06: 24; 2025-03-07: 24; 2025-03-08: 24; 2025-03-09: 24; 2025-03-10: 12; 2025-03-11: OFF; 2025-03-12: OFF; 2025-03-13: OFF; 2025-03-14: OFF; 2025-03-15: OFF; 2025-03-16: OFF; 2025-03-17: 10; 2025-03-18: OFF; 2025-03-19: OFF; 2025-03-20: OFF; 2025-03-21: 9; 2025-03-22: 24; 2025-03-23: 24; 2025-03-24: 24; 2025-03-25: 24; 2025-03-26: 16; 2025-03-27: 24; 2025-03-28: 24; 2025-03-29: 24; 2025-03-30: 16; 2025-03-31: 24; 2025-04-01: 24; 2025-04-02: 21; 2025-04-03: 24; 2025-04-04: 23
24166740 | VSL202425309 | M10R HYPERSOL (AMPIN) | TC | 50 | 2025-02-19 | [9 empty] | 2025-03-05 | 2025-02-19: 6; 2025-02-20: 24; 2025-02-21: 24; 2025-02-22: 24; 2025-02-23: 24; 2025-02-24: 4; 2025-03-05: 51
24166738 | VSL202425310 | M10R HYPERSOL (AMPIN) | TC | 50 | 2025-02-19 | [10 empty] | 2025-02-19: 6; 2025-02-20: 24; 2025-02-21: 24; 2025-02-22: 24; 2025-02-23: 24; 2025-02-24: 4
24166740 | VSL202425309 | M10R HYPERSOL (AMPIN) | TC | 50 | 2025-02-24 | [9 empty] | 2025-03-05 | 2025-02-24: 6; 2025-02-25: 24; 2025-02-26: 24; 2025-03-05: 51
24166738 | VSL202425310 | M10R HYPERSOL (AMPIN) | TC | 50 | 2025-02-24 | [9 empty] | 2025-03-05 | 2025-02-24: 6; 2025-02-25: 24; 2025-02-26: 24; 2025-03-05: 51
24471120 | VSL202425342 | Module from UDAY PH-II line (From IPQC) | TC | 200 | 2025-03-04 | [9 empty] | 2025-05-26 | 2025-03-04: 7; 2025-03-05: 24; 2025-03-06: 5; 2025-03-07: OFF; 2025-03-08: OFF; 2025-03-09: 5; 2025-03-10: 12; 2025-03-11: OFF; 2025-03-12: OFF; 2025-03-13: OFF; 2025-03-14: OFF; 2025-03-15: OFF; 2025-03-16: OFF; 2025-03-17: 6; 2025-03-18: OFF; 2025-03-19: OFF; 2025-03-20: OFF; 2025-03-21: OFF; 2025-03-22: OFF; 2025-03-23: OFF; 2025-03-24: 6; 2025-03-25: OFF; 2025-03-26: OFF; 2025-03-27: OFF; 2025-03-28: OFF; 2025-03-29: OFF; 2025-03-30: OFF; 2025-03-31: OFF; 2025-04-01: OFF; 2025-04-02: OFF; 2025-04-03: OFF; 2025-04-04: OFF; 2025-04-05: OFF; 2025-04-06: OFF; 2025-04-07: OFF; 2025-04-08: OFF; 2025-04-09: OFF; 2025-04-10: OFF; 2025-04-11: OFF; 2025-04-26: 355
24395952 | VSL202425343 | G12R TOPCon (PVEL BOM) | LID | 60 | 2025-03-03 | [9 empty] | 2025-03-14 | 2025-03-03: 5; 2025-03-04: 5; 2025-03-05: 5; 2025-03-06: 5; 2025-03-07: 5; 2025-03-08: 5; 2025-03-09: 5; 2025-03-10: 5; 2025-03-11: 5; 2025-03-12: 5; 2025-03-13: 5; 2025-03-14: 5
24395977 | VSL202425344 | G12R TOPCon (PVEL BOM) | LID | 60 | 2025-03-03 | [9 empty] | 2025-03-14 | 2025-03-03: 5; 2025-03-04: 5; 2025-03-05: 5; 2025-03-06: 5; 2025-03-07: 5; 2025-03-08: 5; 2025-03-09: 5; 2025-03-10: 5; 2025-03-11: 5; 2025-03-12: 5; 2025-03-13: 5; 2025-03-14: 5
24395942 | VSL202425345 | G12R TOPCon (PVEL BOM) | LID | 60 | 2025-03-03 | [9 empty] | 2025-03-14 | 2025-03-03: 5; 2025-03-04: 5; 2025-03-05: 5; 2025-03-06: 5; 2025-03-07: 5; 2025-03-08: 5; 2025-03-09: 5; 2025-03-10: 5; 2025-03-11: 5; 2025-03-12: 5; 2025-03-13: 5; 2025-03-14: 5
24636087 | VSL202425351 | Renewsys EPE+EVA evaluation | LID | 60 | 2025-03-03 | [9 empty] | 2025-03-14 | 2025-03-03: 5; 2025-03-04: 5; 2025-03-05: 5; 2025-03-06: 5; 2025-03-07: 5; 2025-03-08: 5; 2025-03-09: 5; 2025-03-10: 5; 2025-03-11: 5; 2025-03-12: 5; 2025-03-13: 5; 2025-03-14: 5
24636090 | VSL202425348 | Alishan EPE+EVA evaluation | LID | 60 | 2025-03-03 | [9 empty] | 2025-03-14 | 2025-03-03: 5; 2025-03-04: 5; 2025-03-05: 5; 2025-03-06: 5; 2025-03-07: 5; 2025-03-08: 5; 2025-03-09: 5; 2025-03-10: 5; 2025-03-11: 5; 2025-03-12: 5; 2025-03-13: 5; 2025-03-14: 5
24636091 | VSL202425346 | ESun Solar EPE+EVA evaluation | LID | 60 | 2025-03-03 | [9 empty] | 2025-03-14 | 2025-03-03: 5; 2025-03-04: 5; 2025-03-05: 5; 2025-03-06: 5; 2025-03-07: 5; 2025-03-08: 5; 2025-03-09: 5; 2025-03-10: 5; 2025-03-11: 5; 2025-03-12: 5; 2025-03-13: 5; 2025-03-14: 5
24636088 | VSL202425350 | Renewsys EPE+EVA evaluation | PID | 96 | 2025-04-08 | [9 empty] | 2025-04-11 | 2025-04-08: 6; 2025-04-09: 24; 2025-04-10: 24; 2025-04-11: 24; 2025-04-12: 18
24636089 | VSL202425348 | Alishan EPE+EVA evaluation | PID | 96 | 2025-04-08 | [9 empty] | 2025-04-11 | 2025-04-08: 6; 2025-04-09: 24; 2025-04-10: 24; 2025-04-11: 24; 2025-04-12: 18
24636092 | VSL202425347 | ESun Solar EPE+EVA evaluation | PID | 96 | 2025-03-05 | [9 empty] | 2025-03-09 | 2025-03-05: 12; 2025-03-06: 24; 2025-03-07: 24; 2025-03-08: 24; 2025-03-09: 14
24395952 | VSL202425343 | G12R TOPCon (PVEL BOM) | DH | 2000
24395977 | VSL202425344 | G12R TOPCon (PVEL BOM) | TC | 400
24395942 | VSL202425345 | G12R TOPCon (PVEL BOM) | PID | 288
24567303 | VSL202425352 | Stringer 8, Lam 11 UDAY PH-II line (IPQC) | LID | 60 | 2025-03-06 | [9 empty] | 2025-03-14 | 2025-03-06: 5; 2025-03-07: 5; 2025-03-08: 5; 2025-03-09: 5; 2025-03-10: 5; 2025-03-11: 5; 2025-03-12: 5; 2025-03-13: 5; 2025-03-14: 5; 2025-03-15: 5; 2025-03-16: 5; 2025-03-17: 5
24567296 | VSL202425354 | Stringer 8, Lam 8 UDAY PH-II line (IPQC) | LID | 60 | 2025-03-06 | [9 empty] | 2025-03-14 | 2025-03-06: 5; 2025-03-07: 5; 2025-03-08: 5; 2025-03-09: 5; 2025-03-10: 5; 2025-03-11: 5; 2025-03-12: 5; 2025-03-13: 5; 2025-03-14: 5; 2025-03-15: 5; 2025-03-16: 5; 2025-03-17: 5
24567289 | VSL202425355 | Stringer 12, Lam 8 UDAY PH-II line (IPQC) | LID | 60 | 2025-03-06 | [9 empty] | 2025-03-14 | 2025-03-06: 5; 2025-03-07: 5; 2025-03-08: 5; 2025-03-09: 5; 2025-03-10: 5; 2025-03-11: 5; 2025-03-12: 5; 2025-03-13: 5; 2025-03-14: 5; 2025-03-15: 5; 2025-03-16: 5; 2025-03-17: 5
24567319 | VSL202425356 | Stringer 7, Lam 7 UDAY PH-II line (IPQC) | LID | 60 | 2025-03-06 | [9 empty] | 2025-03-14 | 2025-03-06: 5; 2025-03-07: 5; 2025-03-08: 5; 2025-03-09: 5; 2025-03-10: 5; 2025-03-11: 5; 2025-03-12: 5; 2025-03-13: 5; 2025-03-14: 5; 2025-03-15: 5; 2025-03-16: 5; 2025-03-17: 5
24567277 | VSL202425357 | Stringer 10, Lam 8 UDAY PH-II line (IPQC) | LID | 60 | 2025-03-06 | [9 empty] | 2025-03-14 | 2025-03-06: 5; 2025-03-07: 5; 2025-03-08: 5; 2025-03-09: 5; 2025-03-10: 5; 2025-03-11: 5; 2025-03-12: 5; 2025-03-13: 5; 2025-03-14: 5; 2025-03-15: 5; 2025-03-16: 5; 2025-03-17: 5
24567774 | VSL202425358 | UDAY PH-II line (IPQC) | LID | 60 | 2025-03-06 | [9 empty] | 2025-03-14 | 2025-03-06: 5; 2025-03-07: 5; 2025-03-08: 5; 2025-03-09: 5; 2025-03-10: 5; 2025-03-11: 5; 2025-03-12: 5; 2025-03-13: 5; 2025-03-14: 5; 2025-03-15: 5; 2025-03-16: 5; 2025-03-17: 5
24567851 | VSL202425359 | Stringer 9, Lam 6 UDAY PH-II line (IPQC) | LID | 60 | 2025-03-06 | [9 empty] | 2025-03-14 | 2025-03-06: 5; 2025-03-07: 5; 2025-03-08: 5; 2025-03-09: 5; 2025-03-10: 5; 2025-03-11: 5; 2025-03-12: 5; 2025-03-13: 5; 2025-03-14: 5; 2025-03-15: 5; 2025-03-16: 5; 2025-03-17: 5
24559501 | VSL202425360 | UDAY PH-II line (IPQC) | LID | 60 | 2025-03-06 | [9 empty] | 2025-03-14 | 2025-03-06: 5; 2025-03-07: 5; 2025-03-08: 5; 2025-03-09: 5; 2025-03-10: 5; 2025-03-11: 5; 2025-03-12: 5; 2025-03-13: 5; 2025-03-14: 5; 2025-03-15: 5; 2025-03-16: 5; 2025-03-17: 5
24567303 | VSL202425352 | Stringer 8, Lam 11 UDAY PH-II line (IPQC) | DH | 1000 | 2025-06-16 | [10 empty] | 2025-06-16: 7; 2025-06-17: 24; 2025-06-18: 24; 2025-06-19: 24; 2025-06-20: 23; 2025-06-21: 24; 2025-06-22: 24; 2025-06-23: 23; 2025-06-24: 24; 2025-06-25: 23; 2025-06-26: 24; 2025-06-27: 24; 2025-06-28: 24; 2025-06-29: 24; 2025-06-30: 24; 2025-07-01: 24; 2025-07-02: 24; 2025-07-03: 24; 2025-07-04: 24; 2025-07-05: 24
24567296 | VSL202425354 | Stringer 8, Lam 8 UDAY PH-II line (IPQC) | DH | 1000 | 2025-04-26 | [9 empty] | 2025-05-30 | 2025-04-25: 6; 2025-04-26: 24; 2025-04-27: 24; 2025-04-28: 24; 2025-04-29: 24; 2025-04-30: 24; 2025-05-01: OFF; 2025-05-02: 24; 2025-05-03: 24; 2025-05-04: 24; 2025-05-05: 24; 2025-05-06: 24; 2025-05-07: 24; 2025-05-08: 24; 2025-05-09: 24; 2025-05-10: 24; 2025-05-11: 24; 2025-05-12: 24; 2025-05-13: 24; 2025-05-14: 24; 2025-05-15: 24; 2025-05-16: 24; 2025-05-17: 24; 2025-05-18: 24; 2025-05-19: 24; 2025-05-20: 24; 2025-05-21: 24; 2025-05-22: 24; 2025-05-23: 24; 2025-05-24: 24; 2025-05-25: 24; 2025-05-26: 24; 2025-05-27: 24; 2025-05-28: 24; 2025-05-29: 24; 2025-05-30: 202
24567289 | VSL202425355 | Stringer 12, Lam 8 UDAY PH-II line (IPQC) | DH | 1000 | 2025-06-16 | [10 empty] | 2025-06-16: 7; 2025-06-17: 24; 2025-06-18: 24; 2025-06-19: 24; 2025-06-20: 23; 2025-06-21: 24; 2025-06-22: 24; 2025-06-23: 23; 2025-06-24: 24; 2025-06-25: 23; 2025-06-26: 24; 2025-06-27: 24; 2025-06-28: 24; 2025-06-29: 24; 2025-06-30: 24; 2025-07-01: 24; 2025-07-02: 24; 2025-07-03: 24; 2025-07-04: 24; 2025-07-05: 24
24567319 | VSL202425356 | Stringer 7, Lam 7 UDAY PH-II line (IPQC) | DH | 1000 | 2025-04-26 | [9 empty] | 2025-05-30 | 2025-04-25: 6; 2025-04-26: 24; 2025-04-27: 24; 2025-04-28: 24; 2025-04-29: 24; 2025-04-30: 24; 2025-05-01: OFF; 2025-05-02: 24; 2025-05-03: 24; 2025-05-04: 24; 2025-05-05: 24; 2025-05-06: 24; 2025-05-07: 24; 2025-05-08: 24; 2025-05-09: 24; 2025-05-10: 24; 2025-05-11: 24; 2025-05-12: 24; 2025-05-13: 24; 2025-05-14: 24; 2025-05-15: 24; 2025-05-16: 24; 2025-05-17: 24; 2025-05-18: 24; 2025-05-19: 24; 2025-05-20: 24; 2025-05-21: 24; 2025-05-22: 24; 2025-05-23: 24; 2025-05-24: 24; 2025-05-25: 24; 2025-05-26: 24; 2025-05-27: 24; 2025-05-28: 24; 2025-05-29: 24; 2025-05-30: 202
24567277 | VSL202425357 | Stringer 10, Lam 8 UDAY PH-II line (IPQC) | DH | 1000 | 2025-04-26 | [9 empty] | 2025-05-30 | 2025-04-25: 6; 2025-04-26: 24; 2025-04-27: 24; 2025-04-28: 24; 2025-04-29: 24; 2025-04-30: 24; 2025-05-01: off; 2025-05-02: 24; 2025-05-03: 24; 2025-05-04: 24; 2025-05-05: 24; 2025-05-06: 24; 2025-05-07: 24; 2025-05-08: 24; 2025-05-09: 24; 2025-05-10: 24; 2025-05-11: 24; 2025-05-12: 24; 2025-05-13: 24; 2025-05-14: 24; 2025-05-15: 24; 2025-05-16: 24; 2025-05-17: 24; 2025-05-18: 24; 2025-05-19: 24; 2025-05-20: 24; 2025-05-21: 24; 2025-05-22: 24; 2025-05-23: 24; 2025-05-24: 24; 2025-05-25: 24; 2025-05-26: 24; 2025-05-27: 24; 2025-05-28: 24; 2025-05-29: 24; 2025-05-30: 202
24567774 | VSL202425358 | UDAY PH-II line (IPQC) | DH | 1000 | 2025-04-26 | [9 empty] | 2025-05-30 | 2025-04-25: 6; 2025-04-26: 24; 2025-04-27: 24; 2025-04-28: 24; 2025-04-29: 24; 2025-04-30: 24; 2025-05-01: off; 2025-05-02: 24; 2025-05-03: 24; 2025-05-04: 24; 2025-05-05: 24; 2025-05-06: 24; 2025-05-07: 24; 2025-05-08: 24; 2025-05-09: 24; 2025-05-10: 24; 2025-05-11: 24; 2025-05-12: 24; 2025-05-13: 24; 2025-05-14: 24; 2025-05-15: 24; 2025-05-16: 24; 2025-05-17: 24; 2025-05-18: 24; 2025-05-19: 24; 2025-05-20: 24; 2025-05-21: 24; 2025-05-22: 24; 2025-05-23: 24; 2025-05-24: 24; 2025-05-25: 24; 2025-05-26: 24; 2025-05-27: 24; 2025-05-28: 24; 2025-05-29: 24; 2025-05-30: 202
24567851 | VSL202425359 | Stringer 9, Lam 6 UDAY PH-II line (IPQC) | DH | 1000 | 2025-06-16 | [10 empty] | 2025-06-16: 7; 2025-06-17: 24; 2025-06-18: 24; 2025-06-19: 24; 2025-06-20: 23; 2025-06-21: 24; 2025-06-22: 24; 2025-06-23: 23; 2025-06-24: 24; 2025-06-25: 23; 2025-06-26: 24; 2025-06-27: 24; 2025-06-28: 24; 2025-06-29: 24; 2025-06-30: 24; 2025-07-01: 24; 2025-07-02: 24; 2025-07-03: 24; 2025-07-04: 24; 2025-07-05: 24
24559501 | VSL202425360 | UDAY PH-II line (IPQC) | DH | 1000 | 2025-06-16 | [10 empty] | 2025-06-16: 7; 2025-06-17: 24; 2025-06-18: 24; 2025-06-19: 24; 2025-06-20: 23; 2025-06-21: 24; 2025-06-22: 24; 2025-06-23: 23; 2025-06-24: 24; 2025-06-25: 23; 2025-06-26: 24; 2025-06-27: 24; 2025-06-28: 24; 2025-06-29: 24; 2025-06-30: 24; 2025-07-01: 24; 2025-07-02: 24; 2025-07-03: 24; 2025-07-04: 24; 2025-07-05: 24
24079686 | VSL202425266 | G12R Extended Reliability | DH | 1000 | 2025-03-17 | [9 empty] | 2025-05-22 | 2025-03-17: 10; 2025-03-18: OFF; 2025-03-19: OFF; 2025-03-20: OFF; 2025-03-21: 9; 2025-03-22: 24; 2025-03-23: 24; 2025-03-24: 24; 2025-03-25: 24; 2025-03-26: 16; 2025-03-27: 24; 2025-03-28: 24; 2025-03-29: 24; 2025-03-30: 16; 2025-03-31: 24; 2025-04-01: 24; 2025-04-02: 21; 2025-04-03: 24; 2025-04-04: 24; 2025-04-05: 24; 2025-04-06: 24; 2025-04-07: 24; 2025-04-08: 22; 2025-04-09: 20; 2025-04-10: 24; 2025-04-11: 24; 2025-05-22: 502
24079692 | VSL202425268 | G12R Extended Reliability | TC | 200 | 2025-03-17 | [9 empty] | 2025-05-26 | 2025-03-17: 6; 2025-03-18: OFF; 2025-03-19: OFF; 2025-03-20: OFF; 2025-03-21: OFF; 2025-03-22: OFF; 2025-03-23: OFF; 2025-03-24: 6; 2025-03-25: OFF; 2025-03-26: OFF; 2025-03-27: OFF; 2025-03-28: OFF; 2025-03-29: OFF; 2025-03-30: OFF; 2025-03-31: OFF; 2025-04-01: OFF; 2025-04-02: OFF; 2025-04-03: OFF; 2025-04-04: OFF; 2025-04-05: OFF; 2025-04-06: OFF; 2025-04-07: OFF; 2025-04-08: off; 2025-04-09: off; 2025-04-10: off; 2025-04-11: off; 2025-04-26: 408
24636092 | VSL202425347 | ESun Solar EPE+EVA evaluation | PID | 96 | 2025-03-17 | [9 empty] | 2025-03-25 | 2025-03-17: 10; 2025-03-18: OFF; 2025-03-19: OFF; 2025-03-20: OFF; 2025-03-21: 9; 2025-03-22: 24; 2025-03-23: 24; 2025-03-24: 24; 2025-03-25: 6
24793376 | VSL202425367 | M10R HYPERSOL (ENERPARC) | HF | 10 | 2025-04-02 | [9 empty] | 2025-07-09 | 2025-04-02: 6; 2025-04-03: 24; 2025-04-04: 24; 2025-04-05: 12; 2025-04-06: 6; 2025-04-07: OFF; 2025-04-08: 6; 2025-04-09: OFF; 2025-04-10: 12; 2025-04-11: 24; 2025-07-09: 126; 2025-07-10: end
24713456 | VSL202425369 | M10R HYPERSOL (GA INFRA) | DH | 200 | 2025-04-02 | [10 empty] | 2025-04-02: 8; 2025-04-03: 24; 2025-04-04: 24; 2025-04-05: 24; 2025-04-06: 24; 2025-04-07: 24; 2025-04-08: 24; 2025-04-09: 24; 2025-04-10: 24
24713371 | VSL202425371 | M10R HYPERSOL (GA INFRA) | PID | 96 | 2025-04-02 | [10 empty] | 2025-04-02: 8; 2025-04-03: 24; 2025-04-04: 24; 2025-04-05: 24; 2025-04-06: 16
24713222 | VSL202425372 | M10R HYPERSOL (GA INFRA) | TC | 200 | 2025-04-02 | [10 empty] | 2025-04-02: 8; 2025-04-03: 24; 2025-04-04: 24; 2025-04-05: 24; 2025-04-06: 24; 2025-04-07: 24; 2025-04-08: 24; 2025-04-09: 24; 2025-04-10: 24; 2025-04-11: 24; 2025-04-12: 196
24636087 | VSL202425351 | Renewsys EPE+EVA evaluation | DH | 1000 | 2025-04-26 | [9 empty] | 2025-06-11 | 2025-04-26: 16; 2025-04-27: 24; 2025-04-28: 24; 2025-04-29: 24; 2025-04-30: 24; 2025-05-01: off; 2025-05-02: 24; 2025-05-03: 24; 2025-05-04: 24; 2025-05-05: 24; 2025-05-06: 24; 2025-05-07: 24; 2025-05-08: 24; 2025-05-09: 24; 2025-05-10: 24; 2025-05-11: 24; 2025-05-12: 24; 2025-05-13: 24; 2025-05-14: 24; 2025-05-15: 24; 2025-05-16: 24; 2025-05-17: 24; 2025-05-18: 24; 2025-05-19: 24; 2025-05-20: 24; 2025-05-21: 24; 2025-05-22: 24; 2025-05-23: 24; 2025-05-24: 24; 2025-05-25: 24; 2025-05-26: 24; 2025-05-27: 24; 2025-05-28: 24; 2025-05-29: 24; 2025-05-30: 24; 2025-05-31: 24; 2025-06-01: 24; 2025-06-02: 24; 2025-06-03: 24; 2025-06-04: 24; 2025-06-05: 24; 2025-06-06: 9; 2025-06-07: off; 2025-06-08: 8; 2025-06-09: 24; 2025-06-10: 24; 2025-06-11: end
24636090 | VSL202425348 | Alishan EPE+EVA evaluation | DH | 1000 | 2025-04-26 | [9 empty] | 2025-06-11 | 2025-04-26: 16; 2025-04-27: 24; 2025-04-28: 24; 2025-04-29: 24; 2025-04-30: 24; 2025-05-01: off; 2025-05-02: 24; 2025-05-03: 24; 2025-05-04: 24; 2025-05-05: 24; 2025-05-06: 24; 2025-05-07: 24; 2025-05-08: 24; 2025-05-09: 24; 2025-05-10: 24; 2025-05-11: 24; 2025-05-12: 24; 2025-05-13: 24; 2025-05-14: 24; 2025-05-15: 24; 2025-05-16: 24; 2025-05-17: 24; 2025-05-18: 24; 2025-05-19: 24; 2025-05-20: 24; 2025-05-21: 24; 2025-05-22: 24; 2025-05-23: 24; 2025-05-24: 24; 2025-05-25: 24; 2025-05-26: 24; 2025-05-27: 24; 2025-05-28: 24; 2025-05-29: 24; 2025-05-30: 24; 2025-05-31: 24; 2025-06-01: 24; 2025-06-02: 24; 2025-06-03: 24; 2025-06-04: 24; 2025-06-05: 24; 2025-06-06: 9; 2025-06-07: off; 2025-06-08: 8; 2025-06-09: 24; 2025-06-10: 24; 2025-06-11: end
24636091 | VSL202425346 | ESun Solar EPE+EVA evaluation | DH | 1000 | 2025-04-26 | [9 empty] | 2025-06-11 | 2025-04-26: 16; 2025-04-27: 24; 2025-04-28: 24; 2025-04-29: 24; 2025-04-30: 24; 2025-05-01: off; 2025-05-02: 24; 2025-05-03: 24; 2025-05-04: 24; 2025-05-05: 24; 2025-05-06: 24; 2025-05-07: 24; 2025-05-08: 24; 2025-05-09: 24; 2025-05-10: 24; 2025-05-11: 24; 2025-05-12: 24; 2025-05-13: 24; 2025-05-14: 24; 2025-05-15: 24; 2025-05-16: 24; 2025-05-17: 24; 2025-05-18: 24; 2025-05-19: 24; 2025-05-20: 24; 2025-05-21: 24; 2025-05-22: 24; 2025-05-23: 24; 2025-05-24: 24; 2025-05-25: 24; 2025-05-26: 24; 2025-05-27: 24; 2025-05-28: 24; 2025-05-29: 24; 2025-05-30: 24; 2025-05-31: 24; 2025-06-01: 24; 2025-06-02: 24; 2025-06-03: 24; 2025-06-04: 24; 2025-06-05: 24; 2025-06-06: 9; 2025-06-07: off; 2025-06-08: 8; 2025-06-09: 24; 2025-06-10: 24; 2025-06-11: end
24636089 | VSL202425348 | Alishan EPE+EVA evaluation | PID | 96 | 2025-04-08 | [9 empty] | 2025-04-12 | 2025-04-08: 6; 2025-04-09: 20; 2025-04-10: 24; 2025-04-11: 24; 2025-04-12: 22
24636088 | VSL202425350 | Renewsys EPE+EVA evaluation | PID | 96 | 2025-04-08 | [9 empty] | 2025-04-12 | 2025-04-08: 6; 2025-04-09: 20; 2025-04-10: 24; 2025-04-11: 24; 2025-04-12: 22
25017935 | VSL202425381 | Tongwei M10R Hypersol cell trial | LID | 60 | 2025-04-17 | [9 empty] | 2025-04-28
25017936 | VSL202425382 | Tongwei M10R Hypersol cell trial | PID | 96 | 2025-04-26 | [9 empty] | 2025-04-29 | 2025-04-26: 24; 2025-04-27: 24; 2025-04-28: 24; 2025-04-29: 24
25017937 | VSL202425383 | Tongwei M10R Hypersol cell trial | DH | 1000 | 2025-07-02
25019644 | VSL202425384 | DMEGC M10R Hypersol cell trial | LID | 60 | 2025-04-17 | [9 empty] | 2025-04-28 | 2025-04-17: 5; 2025-04-18: 5; 2025-04-19: 5; 2025-04-20: 5; 2025-04-21: 5; 2025-04-22: 5; 2025-04-23: 5; 2025-04-24: 5; 2025-04-25: 5; 2025-04-26: 5; 2025-04-27: 5; 2025-04-28: 5; 2025-07-02: 8; 2025-07-03: 24; 2025-07-04: 24; 2025-07-05: 24
25019645 | VSL202425385 | DMEGC M10R Hypersol cell trial | PID | 96 | 2025-04-26 | [9 empty] | 2025-04-29 | 2025-04-26: 24; 2025-04-27: 24; 2025-04-28: 24; 2025-04-29: 24
25019646 | VSL202425386 | DMEGC M10R Hypersol cell trial | DH | 1000 | 2025-07-02 | [10 empty] | 2025-07-02: 8; 2025-07-03: 24; 2025-07-04: 24; 2025-07-05: 24
24848800 | VSL202425373 | QC SOLAR BLK DIODE 2.0 | DH | 1000 | 2025-04-16 | [9 empty] | 2025-06-11 | 2025-04-16: 12; 2025-04-17: 24; 2025-04-18: 9; 2025-04-19: off; 2025-04-20: off; 2025-04-21: off; 2025-04-22: off; 2025-04-23: off; 2025-04-24: off; 2025-04-25: 6; 2025-04-26: 24; 2025-04-27: 24; 2025-04-28: 24; 2025-04-29: 24; 2025-04-30: 24; 2025-05-01: off; 2025-05-02: 24; 2025-05-03: 24; 2025-05-04: 24; 2025-05-05: 24; 2025-05-06: 24; 2025-05-07: 24; 2025-05-08: 24; 2025-05-09: 24; 2025-05-10: 24; 2025-05-11: 24; 2025-05-12: 24; 2025-05-13: 24; 2025-05-14: 24; 2025-05-15: 24; 2025-05-16: 24; 2025-05-17: 24; 2025-05-18: 24; 2025-05-19: 24; 2025-05-20: 24; 2025-05-21: 24; 2025-05-22: 24; 2025-05-23: 24; 2025-05-24: 24; 2025-05-25: 24; 2025-05-26: 24; 2025-05-27: 24; 2025-05-28: 24; 2025-05-29: 24; 2025-05-30: 24; 2025-05-31: 8; 2025-06-01: 14; 2025-06-02: 24; 2025-06-03: 24; 2025-06-04: 24; 2025-06-05: 24; 2025-06-06: 9; 2025-06-07: off; 2025-06-08: 8; 2025-06-09: 24; 2025-06-10: 5; 2025-06-11: hold
24859051 | VSL202425377 | UKT BLK DIODE (Modified) | DH | 1000 | 2025-04-16 | [9 empty] | 2025-06-11 | 2025-04-16: 12; 2025-04-17: 24; 2025-04-18: 9; 2025-04-19: off; 2025-04-20: off; 2025-04-21: off; 2025-04-22: off; 2025-04-23: off; 2025-04-24: off; 2025-04-25: 6; 2025-04-26: 24; 2025-04-27: 24; 2025-04-28: 24; 2025-04-29: 24; 2025-04-30: 24; 2025-05-01: off; 2025-05-02: 24; 2025-05-03: 24; 2025-05-04: 24; 2025-05-05: 24; 2025-05-06: 24; 2025-05-07: 24; 2025-05-08: 24; 2025-05-09: 24; 2025-05-10: 24; 2025-05-11: 24; 2025-05-12: 24; 2025-05-13: 24; 2025-05-14: 24; 2025-05-15: 24; 2025-05-16: 24; 2025-05-17: 24; 2025-05-18: 24; 2025-05-19: 24; 2025-05-20: 24; 2025-05-21: 24; 2025-05-22: 24; 2025-05-23: 24; 2025-05-24: 24; 2025-05-25: 24; 2025-05-26: 24; 2025-05-27: 24; 2025-05-28: 24; 2025-05-29: 24; 2025-05-30: 24; 2025-05-31: 8; 2025-06-01: 14; 2025-06-02: 24; 2025-06-03: 24; 2025-06-04: 24; 2025-06-05: 24; 2025-06-06: 9; 2025-06-07: off; 2025-06-08: 8; 2025-06-09: 24; 2025-06-10: 5; 2025-06-11: hold
24988445 | VSL202526006 | ACME M10R HYPERSOL | Anti PID | 96
24988559 | VSL202526007 | ACME M10R HYPERSOL | PID | 96
24988692 | VSL202526008 | ACME M10R HYPERSOL | LETID | 162
24923318 | VSL202425379 | Fasto White Sealant trial | DH | 1000 | 2025-05-16 | [10 empty] | 2025-05-16: 12; 2025-05-17: 24; 2025-05-18: 24; 2025-05-19: 24; 2025-05-20: 24; 2025-05-21: 24; 2025-05-22: 24; 2025-05-23: 24; 2025-05-24: 24; 2025-05-25: 24; 2025-05-26: 24; 2025-05-27: 24; 2025-05-28: 24; 2025-05-29: 24; 2025-05-30: 24; 2025-05-31: 8; 2025-06-01: 14; 2025-06-02: 24; 2025-06-03: 24; 2025-06-04: 24; 2025-06-05: 24; 2025-06-06: 9; 2025-06-07: off; 2025-06-08: 8; 2025-06-09: 24; 2025-06-10: 24; 2025-06-11: 24; 2025-06-12: 19; 2025-06-13: 24; 2025-06-14: 22; 2025-06-15: 24; 2025-06-16: 22; 2025-06-17: 24; 2025-06-18: 24; 2025-06-19: 24; 2025-06-20: 23; 2025-06-21: 24; 2025-06-22: 24; 2025-06-23: 23; 2025-06-24: 24; 2025-06-25: 23; 2025-06-26: 24; 2025-06-27: 24; 2025-06-28: 24; 2025-06-29: 24; 2025-06-30: 24; 2025-07-01: 24; 2025-07-02: 24; 2025-07-03: 24; 2025-07-04: 24; 2025-07-05: 24
24925212 | VSL202425380 | Fasto White Sealant trial | DH | 1000
24857462 | VSL202425376 | UKT BLK DIODE (Modified) | TC | 200 | 2025-05-15 | [10 empty] | 2025-05-15: 8; 2025-05-16: 12; 2025-05-17: 12; 2025-05-18: 12; 2025-05-19: 12; 2025-05-20: 12; 2025-05-21: 12; 2025-05-22: 12; 2025-05-23: 12; 2025-05-24: 12; 2025-05-25: 12; 2025-05-26: 12; 2025-05-27: 12; 2025-05-28: 12; 2025-05-29: 12; 2025-05-30: 12; 2025-05-31: OFF; 2025-06-01: OFF; 2025-06-02: OFF; 2025-06-03: OFF; 2025-06-04: 12; 2025-06-05: 12; 2025-06-06: off
25112301 | VSL202526033 | Toyo Cell (TOPCon) evaluation : 2 times | PID | 96 | 2025-05-29 | [9 empty] | 2025-06-03 | 2025-05-29: 11; 2025-05-30: 24; 2025-05-31: 8; 2025-06-01: 14; 2025-06-02: 24; 2025-06-03: 24
25112300 | VSL202526032 | Toyo Cell (TOPCon) evaluation | DH | 1000 | 2025-05-29 | [10 empty] | 2025-05-29: 11; 2025-05-30: 24; 2025-05-31: 8; 2025-06-01: 14; 2025-06-02: 24; 2025-06-03: 24; 2025-06-04: 24; 2025-06-05: 24; 2025-06-06: off; 2025-06-07: off; 2025-06-08: 8; 2025-06-09: 24; 2025-06-10: 24; 2025-06-11: 24; 2025-06-12: 19; 2025-06-13: 24; 2025-06-14: 22; 2025-06-15: 24; 2025-06-16: 22; 2025-06-17: 24; 2025-06-18: 24; 2025-06-19: 24; 2025-06-20: 23; 2025-06-21: 24; 2025-06-22: 24; 2025-06-23: 23; 2025-06-24: 24; 2025-06-25: 23; 2025-06-26: 24; 2025-06-27: 24; 2025-06-28: 24; 2025-06-29: 24; 2025-06-30: 24; 2025-07-01: 24; 2025-07-02: 24; 2025-07-03: 24; 2025-07-04: 24; 2025-07-05: 24
25087863 | VSL202526010 | PT Bintan Cell Reliability Test | PID | 96 | 2025-05-29 | [9 empty] | 2025-06-03 | 2025-05-29: 11; 2025-05-30: 24; 2025-05-31: 8; 2025-06-01: 14; 2025-06-02: 24; 2025-06-03: 24
25087787 | VSL202526009 | PT Bintan Cell Reliability Test | LID | 60 | 2025-06-13 | [9 empty] | 2025-06-24 | 2025-06-13: 5; 2025-06-14: 5; 2025-06-15: 5; 2025-06-16: 5; 2025-06-17: 5; 2025-06-18: 5; 2025-06-19: 5; 2025-06-20: 5; 2025-06-21: 5; 2025-06-22: 5; 2025-06-23: 5; 2025-06-24: 5; 2025-06-25: END
24848547 | VSL202425378 | UKT BLK DIODE (Modified) | TC | 200 | 2025-05-15 | [9 empty] | 2025-06-06 | 2025-05-15: 8; 2025-05-16: 12; 2025-05-17: 12; 2025-05-18: 12; 2025-05-19: 12; 2025-05-20: 12; 2025-05-21: 12; 2025-05-22: 12; 2025-05-23: 12; 2025-05-24: 12; 2025-05-25: 12; 2025-05-26: 12; 2025-05-27: 12; 2025-05-28: 12; 2025-05-29: 12; 2025-05-30: 12; 2025-05-31: OFF; 2025-06-01: OFF; 2025-06-02: OFF; 2025-06-03: OFF; 2025-06-04: 12; 2025-06-05: 12; 2025-06-06: 208; 2025-06-07: END
50872159 | VSL202526035 | SemCorp G2B Module Failure Analysis | PID | 192 | 2025-05-16
25019645 | VSL202425385 | DMEGC M10R Hypersol cell trial (2nd time) | PID | 96 | 2025-07-02 | [10 empty] | 2025-07-02: 8; 2025-07-03: 24; 2025-07-04: 24; 2025-07-05: 24
25017936 | VSL202425382 | Tongwei M10R Hypersol cell trial (2nd time) | PID | 96 | 2025-07-02 | [10 empty] | 2025-07-02: 8; 2025-07-03: 24; 2025-07-04: 24; 2025-07-05: 24
25089372 | VSL202526030 | Bbetter Low GSM Trial (420F,400B) | LID | 60 | 2025-05-20 | [9 empty] | 2025-05-31 | 2025-05-20: 5; 2025-05-21: 5; 2025-05-22: 5; 2025-05-23: 5; 2025-05-24: 5; 2025-05-25: 5; 2025-05-26: 5; 2025-05-27: 5; 2025-05-28: 5; 2025-05-29: 5; 2025-05-30: 5; 2025-05-31: 5
25089365 | VSL202526023 | Cybrid Low GSM Trial (420F,400B) | LID | 60 | 2025-05-20 | [9 empty] | 2025-05-31 | 2025-05-20: 5; 2025-05-21: 5; 2025-05-22: 5; 2025-05-23: 5; 2025-05-24: 5; 2025-05-25: 5; 2025-05-26: 5; 2025-05-27: 5; 2025-05-28: 5; 2025-05-29: 5; 2025-05-30: 5; 2025-05-31: 5
25089363 | VSL202526021 | Cybrid Low GSM Trial (420F,400B) | LID | 60 | 2025-05-20 | [9 empty] | 2025-05-31 | 2025-05-20: 5; 2025-05-21: 5; 2025-05-22: 5; 2025-05-23: 5; 2025-05-24: 5; 2025-05-25: 5; 2025-05-26: 5; 2025-05-27: 5; 2025-05-28: 5; 2025-05-29: 5; 2025-05-30: 5; 2025-05-31: 5
25089370 | VSL202526028 | Bbetter Low GSM Trial (420F,400B) | LID | 60 | 2025-05-20 | [9 empty] | 2025-05-31 | 2025-05-20: 5; 2025-05-21: 5; 2025-05-22: 5; 2025-05-23: 5; 2025-05-24: 5; 2025-05-25: 5; 2025-05-26: 5; 2025-05-27: 5; 2025-05-28: 5; 2025-05-29: 5; 2025-05-30: 5; 2025-05-31: 5
25112299 | VSL202526031 | Toyo Cell (TOPCon) evaluation | LID | 60 | 2025-05-20 | [9 empty] | 2025-05-31 | 2025-05-20: 5; 2025-05-21: 5; 2025-05-22: 5; 2025-05-23: 5; 2025-05-24: 5; 2025-05-25: 5; 2025-05-26: 5; 2025-05-27: 5; 2025-05-28: 5; 2025-05-29: 5; 2025-05-30: 5; 2025-05-31: 5
72149637 | VSL202526016 | IPQC Module (SML+DML+TC50+HF10) | TC | 50 | 2025-05-19 | [9 empty] | 2025-05-29 | 2025-05-19: 8; 2025-05-20: 12; 2025-05-21: 12; 2025-05-22: 12; 2025-05-23: 12; 2025-05-24: 12; 2025-05-25: 12; 2025-05-26: 12; 2025-05-27: 12; 2025-05-28: 12; 2025-05-29: 12
72238923 | VSL202526015 | IPQC Yellow Spot on Ribbon | DH | 1000 | 2025-06-16 | [10 empty] | 2025-06-16: 7; 2025-06-17: 24; 2025-06-18: 24; 2025-06-19: 24; 2025-06-20: 23; 2025-06-21: 24; 2025-06-22: 24; 2025-06-23: 23; 2025-06-24: 24; 2025-06-25: 23; 2025-06-26: 24; 2025-06-27: 24; 2025-06-28: 24; 2025-06-29: 24; 2025-06-30: 24; 2025-07-01: 24; 2025-07-02: 24; 2025-07-03: 24; 2025-07-04: 24; 2025-07-05: 24
25089372 | VSL202526030 | Bbetter Low GSM Trial (420F,400B) | PID | 96 | 2025-06-12 | [9 empty] | 2025-06-16 | 2025-06-12: 7; 2025-06-13: 24; 2025-06-14: 22; 2025-06-15: 24; 2025-06-16: 19; 2025-06-17: END
25089365 | VSL202526023 | Cybrid Low GSM Trial (420F,400B) | PID | 96 | 2025-06-12 | [9 empty] | 2025-06-16 | 2025-06-12: 7; 2025-06-13: 24; 2025-06-14: 22; 2025-06-15: 24; 2025-06-16: 19; 2025-06-17: END
25089363 | VSL202526021 | Cybrid Low GSM Trial (420F,400B) | DH | 1000 | 2025-06-12 | [10 empty] | 2025-06-12: 7; 2025-06-13: 24; 2025-06-14: 22; 2025-06-15: 24; 2025-06-16: 22; 2025-06-17: 24; 2025-06-18: 24; 2025-06-19: 24; 2025-06-20: 23; 2025-06-21: 24; 2025-06-22: 24; 2025-06-23: 23; 2025-06-24: 24; 2025-06-25: 23; 2025-06-26: 24; 2025-06-27: 24; 2025-06-28: 24; 2025-06-29: 24; 2025-06-30: 24; 2025-07-01: 24; 2025-07-02: 24; 2025-07-03: 24; 2025-07-04: 24; 2025-07-05: 24
25089370 | VSL202526028 | Bbetter Low GSM Trial (420F,400B) | DH | 1000 | 2025-06-12
25112301 | VSL202526033 | Toyo Cell (TOPCon) evaluation : 2 times | PID | 96 | 2025-06-16 | [9 empty] | 2025-06-20 | 2025-06-16: 7; 2025-06-17: 24; 2025-06-18: 24; 2025-06-19: 24; 2025-06-20: 17; 2025-06-21: END
72309509 | VSL202526114 | IPQC PID Test Modules : Jun '25 | PID | 96 | 2025-06-06 | [9 empty] | 2025-06-11 | 2025-06-06: 24; 2025-06-07: off; 2025-06-08: 8; 2025-06-09: 24; 2025-06-10: 16; 2025-06-11: 24
72304210 | VSL202526115 | IPQC PID Test Modules : Jun '25 | PID | 96 | 2025-06-06 | [9 empty] | 2025-06-11 | 2025-06-06: 24; 2025-06-07: off; 2025-06-08: 8; 2025-06-09: 24; 2025-06-10: 16; 2025-06-11: 24
25263837 | VSL202526116 | IPQC PID Test Modules : Jun '25 | PID | 96 | 2025-06-06 | [9 empty] | 2025-06-11 | 2025-06-06: 24; 2025-06-07: off; 2025-06-08: 8; 2025-06-09: 24; 2025-06-10: 16; 2025-06-11: 24
25264958 | VSL202526117 | IPQC PID Test Modules : Jun '25 | PID | 96 | 2025-06-06 | [9 empty] | 2025-06-11 | 2025-06-06: 24; 2025-06-07: off; 2025-06-08: 8; 2025-06-09: 24; 2025-06-10: 16; 2025-06-11: 24
25273922 | VSL202526118 | Hangzhou First Low GSM Trial (420F,400B) | LID | 60 | 2025-06-13 | [10 empty] | 2025-06-13: 5; 2025-06-14: 5; 2025-06-15: 5; 2025-06-16: 5; 2025-06-17: 5; 2025-06-18: 5; 2025-06-19: 5; 2025-06-20: 5; 2025-06-21: 5; 2025-06-22: 5; 2025-06-23: 5; 2025-06-24: 5; 2025-06-25: END
25273923 | VSL202526119 | Hangzhou First Low GSM Trial (420F,400B) | PID | 96 | 2025-06-12 | [9 empty] | 2025-06-16 | 2025-06-12: 7; 2025-06-13: 24; 2025-06-14: 22; 2025-06-15: 24; 2025-06-16: 19; 2025-06-17: END
25273924 | VSL202526120 | Hangzhou First Low GSM Trial (420F,400B) | DH | 1000 | 2025-06-12 | [10 empty] | 2025-06-12: 7; 2025-06-13: 24; 2025-06-14: 22; 2025-06-15: 24; 2025-06-16: 22; 2025-06-17: 24; 2025-06-18: 24; 2025-06-19: 24; 2025-06-20: 23; 2025-06-21: 24; 2025-06-22: 24; 2025-06-23: 23; 2025-06-24: 24; 2025-06-25: 23; 2025-06-26: 24; 2025-06-27: 24; 2025-06-28: 24; 2025-06-29: 24; 2025-06-30: 24; 2025-07-01: 24; 2025-07-02: 24; 2025-07-03: 24; 2025-07-04: 24; 2025-07-05: 24
25273925 | VSL202526121 | Hangzhou First Low GSM Trial (420F,400B) | LID | 60 | 2025-06-13 | [9 empty] | 2025-06-24 | 2025-06-13: 5; 2025-06-14: 5; 2025-06-15: 5; 2025-06-16: 5; 2025-06-17: 5; 2025-06-18: 5; 2025-06-19: 5; 2025-06-20: 5; 2025-06-21: 5; 2025-06-22: 5; 2025-06-23: 5; 2025-06-24: 5; 2025-06-25: END
25273926 | VSL202526122 | Hangzhou First Low GSM Trial (420F,400B) | LID | 60 | Reference
25119247 | VSL202526091 | Sunsure HYPERSOL Internal Reliability Tests | PID | 288 | 2025-06-10 | [10 empty] | 2025-06-10: 12; 2025-06-11: 24; 2025-06-12: 19; 2025-06-13: 24; 2025-06-14: 22; 2025-06-15: 24; 2025-06-16: 22; 2025-06-17: 24; 2025-06-18: 24; 2025-06-19: 24; 2025-06-20: 23; 2025-06-21: 24; 2025-06-22: 24; 2025-06-23: 23; 2025-06-24: 24; 2025-06-25: 23; 2025-06-26: 24; 2025-06-27: 24; 2025-06-28: 24; 2025-06-29: 24; 2025-06-30: 24; 2025-07-01: 24; 2025-07-02: 24; 2025-07-03: 24; 2025-07-04: 24; 2025-07-05: 24
25121350 | VSL202526090 | Sunsure HYPERSOL Internal Reliability Tests | PID | 96 | 2025-06-10 | [9 empty] | 2025-06-16 | 2025-06-10: 12; 2025-06-11: 24; 2025-06-12: 19; 2025-06-13: 24; 2025-06-14: 22; 2025-06-15: 24; 2025-06-16: 10; 2025-06-17: END
25121029 | VSL202526084 | Sunsure HYPERSOL Internal Reliability Tests | LID | 60 | 2025-06-10 | [9 empty] | 2025-06-23 | 2025-06-10: 5; 2025-06-11: 5; 2025-06-12: 5; 2025-06-13: 5; 2025-06-14: 5; 2025-06-15: 5; 2025-06-16: 5; 2025-06-17: 5; 2025-06-18: 5; 2025-06-19: 5; 2025-06-20: 5; 2025-06-21: 5; 2025-06-22: 5; 2025-06-23: 5; 2025-06-24: END
25120989 | VSL202526089 | Sunsure HYPERSOL Internal Reliability Tests | PID | 96 | 2025-06-10 | [9 empty] | 2025-06-16 | 2025-06-10: 12; 2025-06-11: 24; 2025-06-12: 19; 2025-06-13: 24; 2025-06-14: 22; 2025-06-15: 24; 2025-06-16: 10; 2025-06-17: END
25129692 | VSL202526092 | Sunsure HYPERSOL Internal Reliability Tests | TC | 200 | 2025-06-10 | [10 empty] | 2025-06-10: 10; 2025-06-11: 16; 2025-06-12: 16; 2025-06-13: 16; 2025-06-14: 16; 2025-06-15: 16; 2025-06-16: 16; 2025-06-17: 16; 2025-06-18: 16; 2025-06-19: 16; 2025-06-20: 16; 2025-06-21: 16; 2025-06-22: 16; 2025-06-23: 16; 2025-06-24: 16; 2025-06-25: 16; 2025-06-26: 16; 2025-06-27: 16; 2025-06-28: 16; 2025-06-29: 16; 2025-06-30: 16; 2025-07-01: 16; 2025-07-02: 16; 2025-07-03: 16; 2025-07-04: 16; 2025-07-05: 16
25129767 | VSL202526093 | Sunsure HYPERSOL Internal Reliability Tests | DH | 1000 | 2025-06-10 | [10 empty] | 2025-06-10: 12; 2025-06-11: 24; 2025-06-12: 19; 2025-06-13: 24; 2025-06-14: 22; 2025-06-15: 24; 2025-06-16: 22; 2025-06-17: 24; 2025-06-18: 24; 2025-06-19: 24; 2025-06-20: 23; 2025-06-21: 24; 2025-06-22: 24; 2025-06-23: 23; 2025-06-24: 24; 2025-06-25: 23; 2025-06-26: 24; 2025-06-27: 24; 2025-06-28: 24; 2025-06-29: 24; 2025-06-30: 24; 2025-07-01: 24; 2025-07-02: 24; 2025-07-03: 24; 2025-07-04: 24; 2025-07-05: 24
25129647 | VSL202526094 | Sunsure HYPERSOL Internal Reliability Tests (DH 1000+SML) | DH | 1000 | 2025-06-10 | [9 empty] | 2025-06-23 | 2025-06-10: 12; 2025-06-11: 24; 2025-06-12: 19; 2025-06-13: 24; 2025-06-14: 22; 2025-06-15: 24; 2025-06-16: 22; 2025-06-17: 24; 2025-06-18: 24; 2025-06-19: 24; 2025-06-20: 23; 2025-06-21: 24; 2025-06-22: 24; 2025-06-23: 23; 2025-06-24: 24; 2025-06-25: 23; 2025-06-26: 24; 2025-06-27: 24; 2025-06-28: 24; 2025-06-29: 24; 2025-06-30: 24; 2025-07-01: 24; 2025-07-02: 24; 2025-07-03: 24; 2025-07-04: 24; 2025-07-05: 24
25129669 | VSL202526085 | Sunsure HYPERSOL Internal Reliability Tests | LID | 60 | 2025-06-09 | [10 empty] | 2025-06-09: 5; 2025-06-10: 5; 2025-06-11: 5; 2025-06-12: 5; 2025-06-13: 5; 2025-06-14: 5; 2025-06-15: 5; 2025-06-16: 5; 2025-06-17: 5; 2025-06-18: 5; 2025-06-19: 5; 2025-06-20: 5; 2025-06-21: 5; 2025-06-22: 5; 2025-06-23: 5; 2025-06-24: END
25173191 | VSL202526101 | Sunsure HYPERSOL Internal Reliability Tests | LID | 20 | 2025-06-09 | [9 empty] | 2025-06-23 | 2025-06-09: 5; 2025-06-10: 5; 2025-06-11: 5; 2025-06-12: 5; 2025-06-13: 5; 2025-06-14: 5; 2025-06-15: 5; 2025-06-16: 5; 2025-06-17: 5; 2025-06-18: 5; 2025-06-19: 5; 2025-06-20: 5; 2025-06-21: 5; 2025-06-22: 5; 2025-06-23: 5; 2025-06-24: END
25170488 | VSL202526103 | Sunsure HYPERSOL Internal Reliability Tests | LID | 60 | 2025-06-09 | [9 empty] | 2025-06-23 | 2025-06-09: 5; 2025-06-10: 5; 2025-06-11: 5; 2025-06-12: 5; 2025-06-13: 5; 2025-06-14: 5; 2025-06-15: 5; 2025-06-16: 5; 2025-06-17: 5; 2025-06-18: 5; 2025-06-19: 5; 2025-06-20: 5; 2025-06-21: 5; 2025-06-22: 5; 2025-06-23: 5; 2025-06-24: END
25176404 | VSL202526108 | Sunsure HYPERSOL Internal Reliability Tests | LID | 60 | 2025-06-09 | [9 empty] | 2025-06-23 | 2025-06-09: 5; 2025-06-10: 5; 2025-06-11: 5; 2025-06-12: 5; 2025-06-13: 5; 2025-06-14: 5; 2025-06-15: 5; 2025-06-16: 5; 2025-06-17: 5; 2025-06-18: 5; 2025-06-19: 5; 2025-06-20: 5; 2025-06-21: 5; 2025-06-22: 5; 2025-06-23: 5; 2025-06-24: END
25087863 | VSL202526010 | PT Bintan Cell Reliability Test (2 times) | PID | 96 | 2025-06-16 | [9 empty] | 2025-06-20 | 2025-06-16: 7; 2025-06-17: 24; 2025-06-18: 24; 2025-06-19: 24; 2025-06-20: 17; 2025-06-21: END
72149637 | VSL202526016 | IPQC Module (SML+DML+TC50+HF10) | HF | 10 | 2025-06-12 | [9 empty] | 2025-06-22 | 2025-06-12: 12; 2025-06-13: 24; 2025-06-14: 24; 2025-06-15: 24; 2025-06-16: 24; 2025-06-17: 24; 2025-06-18: 23; 2025-06-19: 24; 2025-06-20: 24; 2025-06-21: 24; 2025-06-22: 24; 2025-06-23: END
25321818 | VSL202526123 | HIUV EPE+EVA encapsulant trial | LID | 60 | 2025-06-22 | [10 empty] | 2025-06-22: 5; 2025-06-23: 5; 2025-06-24: 5; 2025-06-25: 5; 2025-06-26: 5; 2025-06-27: 5; 2025-06-28: 5; 2025-06-29: 5; 2025-06-30: 5; 2025-07-01: 5; 2025-07-02: 5; 2025-07-03: 5; 2025-07-04: 5; 2025-07-05: 5
25321819 | VSL202526124 | HIUV EPE+EVA encapsulant trial | PID | 96 | 2025-06-20 | [9 empty] | 2025-06-24 | 2025-06-20: 6; 2025-06-21: 24; 2025-06-22: 24; 2025-06-23: 23; 2025-06-24: 19; 2025-06-25: END
25321820 | VSL202526125 | HIUV EPE+EVA encapsulant trial | DH | 1000 | 2025-06-20 | [10 empty] | 2025-06-20: 6; 2025-06-21: 24; 2025-06-22: 24; 2025-06-23: 23; 2025-06-24: 24; 2025-06-25: 23; 2025-06-26: 24; 2025-06-27: 24; 2025-06-28: 24; 2025-06-29: 24; 2025-06-30: 24; 2025-07-01: 24; 2025-07-02: 24; 2025-07-03: 24; 2025-07-04: 24; 2025-07-05: 24
25176363 | VSL202526109 | Sunsure HYPERSOL Internal Reliability Tests | PID | 96 | 2025-06-14 | [9 empty] | 2025-06-18 | 2025-06-14: 12; 2025-06-15: 24; 2025-06-16: 22; 2025-06-17: 24; 2025-06-18: 14; 2025-06-19: END
25179725 | VSL202526112 | Sunsure HYPERSOL Internal Reliability Tests | PID | 96 | 2025-06-14 | [9 empty] | 2025-06-18 | 2025-06-14: 12; 2025-06-15: 24; 2025-06-16: 22; 2025-06-17: 24; 2025-06-18: 14; 2025-06-19: END
25173127 | VSL202526102 | Sunsure HYPERSOL Internal Reliability Tests | PID | 96 | 2025-06-14 | [9 empty] | 2025-06-18 | 2025-06-14: 12; 2025-06-15: 24; 2025-06-16: 22; 2025-06-17: 24; 2025-06-18: 14; 2025-06-19: END
25173179 | VSL202526106 | Sunsure HYPERSOL Internal Reliability Tests | PID | 96 | 2025-06-14 | [9 empty] | 2025-06-18 | 2025-06-14: 12; 2025-06-15: 24; 2025-06-16: 22; 2025-06-17: 24; 2025-06-18: 14; 2025-06-19: END
24859051 | VSL202425377 | UKT BLK DIODE (Modified) | HF | 10 | 2025-06-18 | [10 empty] | 2025-06-18: 13; 2025-06-19: 24; 2025-06-20: 24; 2025-06-21: 24; 2025-06-22: 24; 2025-06-23: 18; 2025-06-24: 24; 2025-06-25: 24; 2025-06-26: 24; 2025-06-27: 24; 2025-06-28: 24; 2025-06-29: END
72369597 | VSL202526126 | IPQC Lower Lam Cycle module | DH | 1000 | 2025-06-23 | [10 empty] | 2025-06-23: 5; 2025-06-24: 24; 2025-06-25: 23; 2025-06-26: 24; 2025-06-27: 24; 2025-06-28: 24; 2025-06-29: 24; 2025-06-30: 24; 2025-07-01: 24; 2025-07-02: 24; 2025-07-03: 24; 2025-07-04: 24; 2025-07-05: 24
72369575 | VSL202526127 | IPQC Lower Lam Cycle module | DH | 1000 | 2025-06-23 | [10 empty] | 2025-06-23: 5; 2025-06-24: 24; 2025-06-25: 23; 2025-06-26: 24; 2025-06-27: 24; 2025-06-28: 24; 2025-06-29: 24; 2025-06-30: 24; 2025-07-01: 24; 2025-07-02: 24; 2025-07-03: 24; 2025-07-04: 24; 2025-07-05: 24
25151639 | VSL202526132 | Cybrid Raybo UV Down Conversion Film Line Trial (Aiko cell) | DH | 1000 | 2025-07-02 | [10 empty] | 2025-07-02: 8; 2025-07-03: 24; 2025-07-04: 24; 2025-07-05: 24
25353591 | VSL202526128 | Cybrid Raybo UV Down Conversion Film Line Trial (Solarspace cell) | DH | 1000 | 2025-07-02 | [10 empty] | 2025-07-02: 8; 2025-07-03: 24; 2025-07-04: 24; 2025-07-05: 24
25353593 | VSL202526129 | Sunbez EPE+EVA encapsulant trial | LID | 60 | 2025-07-01 | [10 empty] | 2025-07-01: 5; 2025-07-02: 5; 2025-07-03: 5; 2025-07-04: 5; 2025-07-05: 5
25353594 | VSL202526130 | Sunbez EPE+EVA encapsulant trial | PID | 96 | 2025-07-02 | [10 empty] | 2025-07-02: 8; 2025-07-03: 24; 2025-07-04: 24; 2025-07-05: 24
25353595 | VSL202526131 | Sunbez EPE+EVA encapsulant trial | DH | 1000 | 2025-07-02 | [10 empty] | 2025-07-02: 8; 2025-07-03: 24; 2025-07-04: 24; 2025-07-05: 24
25357620 | VSL202526149 | M10R HYPERSOL (GA INFRA) | DH | 400 | 2025-07-01 | [10 empty] | 2025-07-01: 12; 2025-07-02: 24; 2025-07-03: 24; 2025-07-04: 24; 2025-07-05: 24
25359186 | VSL202526150 | M10R HYPERSOL (GA INFRA) | DH | 400 | 2025-07-01 | [10 empty] | 2025-07-01: 12; 2025-07-02: 24; 2025-07-03: 24; 2025-07-04: 24; 2025-07-05: 24
25357399 | VSL202526151 | M10R HYPERSOL (GA INFRA) | PID | 96 | 2025-07-01 | [10 empty] | 2025-07-01: 12; 2025-07-02: 24; 2025-07-03: 24; 2025-07-04: 24; 2025-07-05: 24
25358777 | VSL202526152 | M10R HYPERSOL (GA INFRA) | PID | 96 | 2025-07-01 | [10 empty] | 2025-07-01: 12; 2025-07-02: 24; 2025-07-03: 24; 2025-07-04: 24; 2025-07-05: 24
25238843 | VSL202526133 | Cleanmax HYPERSOL Internal Reliability Tests | LID | 60 | 2025-06-25 | [10 empty] | 2025-06-25: 5; 2025-06-26: 5; 2025-06-27: 5; 2025-06-28: 5; 2025-06-29: 5; 2025-06-30: 5; 2025-07-01: 5; 2025-07-02: 5; 2025-07-03: 5
25239166 | VSL202526134 | Cleanmax HYPERSOL Internal Reliability Tests | PID | 96 | 2025-06-25 | [10 empty] | 2025-06-25: 12; 2025-06-26: 24; 2025-06-27: 24; 2025-06-28: 24; 2025-06-29: 24; 2025-06-30: 24; 2025-07-01: 24; 2025-07-02: 24; 2025-07-03: 24; 2025-07-04: 24; 2025-07-05: 24
25248252 | VSL202526135 | Cleanmax HYPERSOL Internal Reliability Tests | LID | 60 | 2025-06-25 | [10 empty] | 2025-06-25: 5; 2025-06-26: 5; 2025-06-27: 5; 2025-06-28: 5; 2025-06-29: 5; 2025-06-30: 5; 2025-07-01: 5; 2025-07-02: 5; 2025-07-03: 5; 2025-07-04: 5; 2025-07-05: 5
25313260 | VSL202526136 | Cleanmax HYPERSOL Internal Reliability Tests | LID | 60 | 2025-06-25 | [10 empty] | 2025-06-25: 5; 2025-06-26: 5; 2025-06-27: 5; 2025-06-28: 5; 2025-06-29: 5; 2025-06-30: 5; 2025-07-01: 5; 2025-07-02: 5; 2025-07-03: 5; 2025-07-04: 5; 2025-07-05: 5
25313310 | VSL202526137 | Cleanmax HYPERSOL Internal Reliability Tests | PID | 96 | 2025-06-25 | [10 empty] | 2025-06-25: 12; 2025-06-26: 24; 2025-06-27: 24; 2025-06-28: 24; 2025-06-29: 24; 2025-06-30: 24; 2025-07-01: 24; 2025-07-02: 24; 2025-07-03: 24; 2025-07-04: 24; 2025-07-05: 24
25270829 | VSL202526138 | Cleanmax HYPERSOL Internal Reliability Tests | LID | 60 | 2025-06-25 | [10 empty] | 2025-06-25: 5; 2025-06-26: 5; 2025-06-27: 5; 2025-06-28: 5; 2025-06-29: 5; 2025-06-30: 5; 2025-07-01: 5; 2025-07-02: 5; 2025-07-03: 5; 2025-07-04: 5; 2025-07-05: 5
25310847 | VSL202526139 | Cleanmax HYPERSOL Internal Reliability Tests | PID | 96 | 2025-06-25 | [10 empty] | 2025-06-25: 12; 2025-06-26: 24; 2025-06-27: 24; 2025-06-28: 24; 2025-06-29: 24; 2025-06-30: 24; 2025-07-01: 24; 2025-07-02: 24; 2025-07-03: 24; 2025-07-04: 24; 2025-07-05: 24
25249419 | VSL202526140 | Cleanmax HYPERSOL Internal Reliability Tests | LID | 60 | 2025-06-26 | [10 empty] | 2025-06-26: 5; 2025-06-27: 5; 2025-06-28: 5; 2025-06-29: 5; 2025-06-30: 5; 2025-07-01: 5; 2025-07-02: 5; 2025-07-03: 5; 2025-07-04: 5; 2025-07-05: 5
25249424 | VSL202526141 | Cleanmax HYPERSOL Internal Reliability Tests | PID | 96 | 2025-06-25 | [10 empty] | 2025-06-25: 12; 2025-06-26: 24; 2025-06-27: 24; 2025-06-28: 24; 2025-06-29: 24; 2025-06-30: 24; 2025-07-01: 24; 2025-07-02: 24; 2025-07-03: 24; 2025-07-04: 24; 2025-07-05: 24
25249390 | VSL202526142 | Cleanmax HYPERSOL Internal Reliability Tests | PID | 96 | 2025-06-30
25338380 | VSL202526143 | Cleanmax HYPERSOL Internal Reliability Tests | LID | 60 | 2025-06-26 | [10 empty] | 2025-06-26: 5; 2025-06-27: 5; 2025-06-28: 5; 2025-06-29: 5; 2025-06-30: 5; 2025-07-01: 5; 2025-07-02: 5; 2025-07-03: 5; 2025-07-04: 5; 2025-07-05: 5
25336519 | VSL202526144 | Cleanmax HYPERSOL Internal Reliability Tests | LID | 60 | 2025-06-26 | [10 empty] | 2025-06-26: 5; 2025-06-27: 5; 2025-06-28: 5; 2025-06-29: 5; 2025-06-30: 5; 2025-07-01: 5; 2025-07-02: 5; 2025-07-03: 5; 2025-07-04: 5; 2025-07-05: 5
25338967 | VSL202526145 | Cleanmax HYPERSOL Internal Reliability Tests | PID | 96 | 2025-06-30 | [10 empty] | 2025-06-30: 10; 2025-07-01: 24; 2025-07-02: 24; 2025-07-03: 24; 2025-07-04: 24; 2025-07-05: 24
25338894 | VSL202526146 | Cleanmax HYPERSOL Internal Reliability Tests | PID | 96 | 2025-06-30 | [10 empty] | 2025-06-30: 10; 2025-07-01: 24; 2025-07-02: 24; 2025-07-03: 24; 2025-07-04: 24; 2025-07-05: 24
25344642 | VSL202526147 | Cleanmax HYPERSOL Internal Reliability Tests | PID | 96 | 2025-06-30 | [10 empty] | 2025-06-30: 10; 2025-07-01: 24; 2025-07-02: 24; 2025-07-03: 24; 2025-07-04: 24; 2025-07-05: 24
25344659 | VSL202526148 | Cleanmax HYPERSOL Internal Reliability Tests | LID | 60 | 2025-06-26 | [10 empty] | 2025-06-26: 5; 2025-06-27: 5; 2025-06-28: 5; 2025-06-29: 5; 2025-06-30: 5; 2025-07-01: 5; 2025-07-02: 5; 2025-07-03: 5; 2025-07-04: 5; 2025-07-05: 5
25273925 | VSL202526121 | Hangzhou First Low GSM Trial (420F,400B) | TC | 200
23905761 | VSL202425235 | Ronma TOPCon Cell Trial | DH | 1000
HJT SAMPLE-1 |  | EPE+EPE | DH | 1000 | 2025-06-20 | [10 empty] | 2025-06-20: 6; 2025-06-21: 24; 2025-06-22: 24; 2025-06-23: 24; 2025-06-24: 24; 2025-06-25: 24; 2025-06-26: 24; 2025-06-27: 24; 2025-06-28: 24; 2025-06-29: 24; 2025-06-30: 12; 2025-07-01: off; 2025-07-02: 8; 2025-07-03: 24; 2025-07-04: 24; 2025-07-05: 24
HJT SAMPLE-2 |  | EPE+EPE+40MM POE | DH | 1000 | 2025-06-21 | [10 empty] | 2025-06-20: 6; 2025-06-21: 24; 2025-06-22: 24; 2025-06-23: 24; 2025-06-24: 24; 2025-06-25: 24; 2025-06-26: 24; 2025-06-27: 24; 2025-06-28: 24; 2025-06-29: 24; 2025-06-30: 12; 2025-07-01: off; 2025-07-02: 8; 2025-07-03: 24; 2025-07-04: 24; 2025-07-05: 24
HJT SAMPLE-3 |  | EPE+EPE HIB TAPE | DH | 1000 | 2025-06-22 | [10 empty] | 2025-06-20: 6; 2025-06-21: 24; 2025-06-22: 24; 2025-06-23: 24; 2025-06-24: 24; 2025-06-25: 24; 2025-06-26: 24; 2025-06-27: 24; 2025-06-28: 24; 2025-06-29: 24; 2025-06-30: 12; 2025-07-01: off; 2025-07-02: 8; 2025-07-03: 24; 2025-07-04: 24; 2025-07-05: 24
25386587 |  | Sunsure HYPERSOL Internal Reliability Tests | PID | 96
25386594 |  | Sunsure HYPERSOL Internal Reliability Tests | PID | 96
25386583 |  | Sunsure HYPERSOL Internal Reliability Tests | DH | 1000
25386578 |  | Sunsure HYPERSOL Internal Reliability Tests | PID | 288
25386240 |  | Sunsure HYPERSOL Internal Reliability Tests | LID | 20
25385829 |  | Sunsure HYPERSOL Internal Reliability Tests | PID | 96
25386238 |  | Sunsure HYPERSOL Internal Reliability Tests | PID | 96
25386229 |  | Sunsure HYPERSOL Internal Reliability Tests | PID | 96
25385835 |  | Sunsure HYPERSOL Internal Reliability Tests | PID | 96
25386639 |  | Sunsure HYPERSOL Internal Reliability Tests | LeTID | 192
25386618 |  | Sunsure HYPERSOL Internal Reliability Tests | LeTID | 192
25386256 |  | Sunsure HYPERSOL Internal Reliability Tests | LID | 20
25385821 |  | Sunsure HYPERSOL Internal Reliability Tests (DH1000+SML) | DH | 1000
25386577 |  | Sunsure HYPERSOL Internal Reliability Tests | LID | 20
25386584 |  | Sunsure HYPERSOL Internal Reliability Tests | LID | 60
25386617 |  | Sunsure HYPERSOL Internal Reliability Tests | HF | 10
25386605 |  | Sunsure HYPERSOL Internal Reliability Tests | TC | 200
25438399 |  | Sunsure HYPERSOL Internal Reliability Tests | PID | 96
25438419 |  | Sunsure HYPERSOL Internal Reliability Tests | LID | 20
25445298 |  | Sunsure HYPERSOL Internal Reliability Tests | PID | 96
25438056 |  | Sunsure HYPERSOL Internal Reliability Tests | PID | 96
25438634 |  | Sunsure HYPERSOL Internal Reliability Tests | LID | 20
25442344 |  | Sunsure HYPERSOL Internal Reliability Tests | PID | 96